Chapter 3 Scheduling Tasks

Topics:

• Processors and priority list

• Possible goals

• List-processing algorithm

— assumptions

— algorithm

— paradoxical behavior

• Decreasing-time-list algorithm

• Independent Tasks

• Critical-Path schedules

1. Introduction

Example 1. Two people are camping out and wish to cook a simple supper consisting of soup and hamburgers. In order to prepare the supper, several tasks must be performed.

T1: Go to store to buy matches — 10 minutes

T2: Collect firewood — 8 minutes

T3: Light the fire — 6 minutes

T4: Get water from a well — 12 minutes

T5: Cook soup (constant stirring) — 15 minutes

T6: Make hamburgers — 9 minutes.

T7: Cook hamburgers — 7 minutes.

Each task requires only one of the campers and once a task is begun it cannot be interrupted.

(a) How should the work be divided between the two campers?

(b) What is the shortest amount of time it will take for all of the tasks to be completed?

Definitions:

• A processor, such as person or machine that can work on a series of tasks.

• A machine-scheduling problem is to decide how the tasks should be scheduled.

• A priority list is a list of ordering tasks according to some criterion of importance.

• An order-requirement digraph shows which tasks precede other tasks among the collection of tasks making up a job.

Comments:

• In this class, we assume that any of the processors can work on any of 	the tasks for the same time.

• Priority and ordering-requirement are independent. The order here is 	physical order (cook before eat). Sometimes you cannot do the top priority task first (priority is to eat but one has to cook first).

Various goals:

• Minimizing the completion time of the job

• Minimizing the total time that processors are idle

2. List-processing Algorithm

Assumptions:

(1) The number of processors is fixed, and they are labeled.

(2) If a processor starts work on a task, the work on the task will continue without interruption until the task is completed.

(3) No processor stays idle when there is an available task.

(4) An order-requirement digraph is given.

(5) All tasks are arranged in a priority list without tie.

(6) When there are two or more processors available, the processor labeled with the lower number will be assigned first.

The List-processing Algorithm:

It is a heuristic algorithm for assigning tasks to processors.

Repeatedly assign the first ready task on the priority list that has not been assigned to the lowest-numbered processor that is not working on a task.

Example 1(Continue): Construct a digraph then use the list processing algorithm to schedule the tasks.  Graph given in class.

Example 2. The order-requirement digraph of a job is given as the following. The priority list is T1, T2,..., T8. Use the list-processing algorithm to schedule the tasks on two machines.

Machine 1 _________________________________________________

Machine 2

l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_

Time  to complete  job=   			Is it optimal?

Example 3. For the same job, a different priority list may schedule the tasks in a different way.

The order-requirement digraph of a job is given as the following. The list is T8, T7,..., T1. Use the list-processing algorithm to schedule the tasks on two machines.

Machine 1 _________________________________________________

Machine 2

l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_

Time  to complete  job=   			Is it optimal?

Example 4. You will do a job for one of your customers. You drafted an order requirement digraph of the job as the following. Time is in hours. What is the critical path?        What is the minimum time to complete the job?   The priority list is  T1, T2,..., T9. Use the list-processing algorithm to schedule the tasks on three machines.

Time  to complete  job=   			Is it optimal?

What is the idle time for Machine 1?      Machine 2?       Machine 3?

What is the total idle time?

Previous you have been given the priority list, now you will make the priority list based on given criteria.

3. Decreasing-time lists

Decreasing-time-list algorithm:

It is a list-processing algorithm where the priority list is obtained by listing the tasks in decreasing order of their time length. If there is a tie, choose the lower numbered task.

Example 5. The order-requirement digraph is given.

(a) Find the priority list by the method of decreasing-time-list algorithm.

(b) Schedule these tasks on two processors using the decreasing-time-list algorithm.

M1 __________________________________________________________________________

M2	 __________________________________________________________________________

_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_I_I

How much time does it take to complete the job?

While the list-processing algorithm has many good features and works well in many situations, it is obviously not perfect. When you see a large area of idle times, you may modify the algorithm and rearrange the jobs to reduce the completion time. However, by doing modification, you may not schedule the job exactly by the priority. In some situations where ethics issue may rise, extra caution is needed.

Definition: Tasks are independent if they can be performed in any order.

Decreasing-time-list algorithm usually works well when all tasks in a job are independent. The longest possible idle time is no longer than the shortest task time.

Example 6. Given all the task times,

| Task | T1 T2 T3 T4 T5 T6 |
| --- | --- |
| Time | 10 4 5 9 7 7 |

(a) Find the priority list by the method of decreasing-time. If there is a tie, choose the lower numbered task.

(b) Schedule these tasks on two processors using the decreasing-time-list algorithm. Is it optimal?

Machine 1 _________________________________________________

Machine 2

l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_

Although the decreasing-time-list algorithm works well in independent cases, it might not give the optimal solution.

Example 7. Given all the task times,

| Task | T1 T2 T3 T4 T5 |
| --- | --- |
| Time | 10 4 5 9 7 |

(a) Find the priority list by the method of decreasing-time.

(b) Schedule these tasks on two processors using the decreasing-time- list algorithm. Is it optimal?

Machine 1 _________________________________________________

Machine 2

l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_

3. Critical-path Schedule

In example 4(Continue), the paradoxical behavior is related to the way task 9 is scheduled. Task 9 takes long time, 8 hours to complete. Because it is the last task on the priority list, it may be started late and therefore delay the whole job completion (“sticking out” at the right end).

The idea of critical-path schedule is that the tasks on the top of the critical paths should be on the top priority, if our priority is to save time.

Critical-path Schedule is the list-processing algorithm where the priority list is obtained by

Step 1. Find a task that heads a critical path in the order-requirement 	 digraph. If there is a tie, choose the lower numbered task.

Step 2. Place the task found in Step 1 first/next on the priority list.

Step 3. Remove the task found in Step 1 from the order-requirement 	 digraph. Now the residual digraph is the new order- requirement digraph.

Step 4. If all the tasks are in the list, stop. Otherwise go to Step 1 and work on the residual digraph.

Example 8. The order-requirement digraph is given.

(a) Find the priority list by the method of critical-path.

Example 9. The order-requirement digraph is given.

(a) Find the priority list by the method of critical-path.

(b) Schedule these tasks on two processors using the decreasing-time-list algorithm. Is it optimal?

M1 __________________________________________________________________________

M2	 __________________________________________________________________________

l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_l_